## Sheet5
CONSOLIDATED ESTIMATE
34
80

## Rashid
List of Things | Hours
Web Host
-Choose a url | 1 hour
-Import the code | 2 hours
Ability to create profiles
-Use SQL to store Data | 4 hours
Create a front end web
-html | 2 hours
-css | 3 hours
-javascript | 7 hours
Create a back end
-php | N/A
-python/java/c | 10 hours
Implement the API's
-Implement search | 2 hour
-Implement filters | 3 hour
34 hours

## Janice
User Story 3
Steps | Frontend Steps | Backend Steps | Hours
User logs in (via Facebook, Google, etc) |  | Authentication Setup | 5
User preferences (user-filtered preferences: allergies, dietary restriction) |  | Cookie Setup/ Server Setup | 10
Ingredients added (curry-search) |  | Pull data from recipes API | 10
Meals populate (preferences crossed with ingredients) |  | SQL Query | 15
User adds additional filters (filters include servings, ideal sodium amount, time restraint) |  |  | 10
Upon clicking the dish (each dish profile contains photo, description, recipe, instructions) |  | Pull data from database crossed between recipes API and nutritional facts API Database stored on server Produce the UI of the dish profile | 30

## Kenny
USER STORY WORK BREAKDOWN
1. User searches ingredient on the home page
which has a giant search bar in the center:
- Implement search: 1 hour
- Implement filtering (Cuisine, Price, Nutrition, Allergies): 2.5 hours
- Implement storing user preferences in SQL if done on our end: 3 hours
- Implement storing user preferences with cookies if done on their end: 3 hours
- Implement login/authentication via Gmail: 1.5 hours.
2. Results Page showing dishes with that ingredient
- Implement grabbing recipes from database using API: 2 hours
- Good looking UI: 1.5 hours
- Implement ability to filter on results page as well: 1.5 hours
3. Clicking a result will go to the recipe's main page with
ingredients list, description, image, and cooking instructions.
- Use API to grab recipe info: 2 hours
- What if no images provided, get images of all food? 3+ hours*

## Daniel
Part | Time Estimation (Weeks) | notes
User login
User preferenaces are loaded onto the webapp |  | Unknown whether this will be local cookies saved on the user end or settings saved on the webapps end
Search function |  | This will use the API to pull results from other websites
Results Page |  | How will this be displayed? A list? Will this be dynamically loaded or cached?
Filtering |  | We need to have specific values for